## On going Projects
Disclosure of Information on Development Projects for General Public as a Right of the People - 2024/2025
On going Projects as at 01.09.2025 (Project which is awarded on or before 01.09.2025 and work started/ongoing)
Executing Agency |  | : Ministry of Urban Development, Construction and Housing
# | Name of the Project | Total Estimated Project Cost (Rs.Mn.) | Expected Duration of the Project | Location of the Project (Grama Niladhari Division /Divisional Secretariat Division /District Secretariat Division) | Financing Agency (GOSL/ Foreign) | Loan |  | Expected Benefits of the Project | Implementing Agency | Location of Project Management Unit | Project Components/ Activities | Contactor Details |  | Value of the Contract (Rs.Mn.)
[6 empty] | Amount (Rs.Mn.) | Interest Rate (%) |  |  |  |  | Name | Address
1 | Name of the Department/Institution/Project : Si Lanka Land Development Corporation
1 | Maintenance of Main Canals and Lakes: Colombo, Hamilton (Muthurajawela -14.5 km length, Negombo - 7.0 km length), Lunawa (N1, N1 - iii, S1 and S2), Old Dutch (Along the Colombo- Katunayake Expressway (10 Km length from Wattala, Mabole to Ja Ela), Kalu Oya (9Km from Ragama to Kelani River end) | 310 | 12 Months | DSDs in Colombo District, Moratuwa, Wattala, Ja-ela, Mahara, | GOSL | - | - | 1. Improve existing drainage system to facilitate free flow of the canals 2. Creating a green and minimizing of flood environment to the public 3. Establish canal maintenance system, minimizing of flood & green environment to create a high social development 4. Control of solid waste, discharge sewerage and siltation 5. Enhance the health condition of the people living in this area, especially Dengue | SLLDC | SLLDC | Improve, maintenance & development of Canal Network and walkways | Deputy General Manager (D&R) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
2 | Maintenance of Secondary canals and associated Lakes | 102.5 | 12 Months | DSDs in Colombo District |  | - | - |  |  |  |  | Deputy General Manager (D&R) /(WM) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
3 | Maintenance activities in Parliament Upper Catchment of Battaramulla and its surrounding area | 15 | 12 Months | DSDs in Colombo District |  | - | - |  |  |  |  | Deputy General Manager (D&R) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
4 | Maintenance of walkways in Colombo and Suburbs | 80.5 | 12 Months | DSDs in Colombo District |  | - | - |  |  |  |  | Deputy General Manager (D&R) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
5 | Rectification of canal bank protection work along the canals (Gabion Work, Sheet Piling, RRM Walls, RCC walls etc) | 7 | 12 Months | DSDs in Colombo District |  | - | - |  |  |  |  | Deputy General Manager (D&R) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
6 | Operation and Maintenance of pumping station at Peliyagoda | 7 | 12 Months | DSDs in Colombo District |  | - | - | Minimizing of flood issues in Peliyagoda Area |  |  | Improvement of Drainage System & taking remedial measures for the flood related issues | Deputy General Manager (D&R) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
9 | Maintenance of walkways in Colombo and Suburbs | 80.5 | 12 Months | Suwatha Uyana , Kadawatha | Treasury | - | - | Promoting mental health standards and, ultimately, improving public health |  | SLLDC | Canal Surface Clearing Canal Banks Clearing Canal Inspection Turf Cutting Maintenance of O & M Road , Electricity bills (Gymnasium/ GS Office / Jogging path and Children’s Play Area) | Deputy General Manager (Construction) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
10 | Operating and Maintenance of Sewerage Pump House at Pelangastuduwa | 2.5 | 12 Months | Pelangastuduwa, Borella. | Treasury | - | - | Maintain the proper hygiene of the environment of the city |  |  | Operating and Maintenance of Sewerage Pump House | Deputy General Manager (Construction) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
11 | Kolonnawa Storm Water Drainage & Environment Improvement Project (Design, Implementation and Maintenance) | 8300 | 2018-2027 | Kolonnawa Divisional Secretariat Area & Kotikawatta - Mulleriyawa Grama Niladhari Division | Treasury | - | - | 1. Enhanced land value due to flood mitigation 2.Protect commercial and business activities from inundation 3.Reduction in flood damage 4.Minimizing water and land pollution by regulating solid and liquid waste disposal. 5. Improve the quality of Environment due to regular systematic canal maintenance and waste disposal. |  |  | Formation of Thuppawela lake, Construction of box culverts 1.Canal improvements with earthen and lining canal (Concrete, Gabion, Random Rubble Masonry and Sheet Pile) 2.Widening of road crossing structures. 3.Creation of retention / detention ponds. 4.Construction of pump station. 5. Formation of operation and maintenance roads with side drains, catch pits and sluiceways. 6. Safe guard the natural storm water storage areas. 7. Canal Maintenance. | Deputy General Manager (D&R/WM & Construction) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
12 | Restoration of banks of Colombo canals using Soft banking approach Stage I Kotte Canal | 0.5 | 1Year | Kotte | GOSL | - | - | Flood Mitigation by improving storm water discharge |  |  | Improve the Canal bank by Soft Banking method | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
13 | Maintenance of Beira Lake water body and water quality improvement | 29 | 1Year | Colombo |  | - | - | Cleanness, Beautification , Oder Control, Water Quality Improvement |  |  | Clean the water surface Placing Floating Treatment Wetlands Biological treatment method | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
14 | Water Quality Improvements in Colombo Canal System | 8 | 1 year | CMC area,Kotte,Maharagama, Kolonnawa,Kaduwela |  | - | - | Industrial waste water management for pollution control |  |  | Water Quality monitoring and reporting Develop a water quality management plan | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
15 | Wetland encroachment Prevention Programmed | 12 | 1 Year | Gothatuwa Madinnagoda |  | - | - | Prevention of Encroachments of the wetland |  |  | Construction of a walking path around the marsh | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
16 | Development of Gothatuwa wetland Park | 73 | 3 Years | Gothatuwa Madinnagoda |  | - | - | Urban Flood Management |  |  | Formation of Encroachment Barrier Fixing of chainlink fence around the government acquired land boundary | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
17 | Conducting CEPA activities for Wetland Conservation & Low Land Development | 5 | 1 year | Colombo Wetlands |  | - | - | To raise the awareness on Wetlands |  |  | Conducting Awareness Programmes Preparation of Flyers,Hordings Conducting school Programmes Conducting webinars on biodiversity | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
18 | Wetland carbon sequestration study | 5 | 12 Months | DSDs in Colombo District |  | - | - | Increased climate change mitigation through Carbon sequestration |  |  | Increased climate change mitigation through Carbon sequestration, Increased significance of Colombo wetlands in the aspect of climate change mitigation | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
19 | Collection of Hydro Meteorological data | 12 | 12 Months | Colombo basin, Ja- Ela basin, Mudun Ela basin, Kolonnawa basin, Bolgoda basin |  | - | - | 1. Data collection for design calibration works. |  |  | 1. Operate & maintain the data collection & storing mechanism of manual water level measurement system 2. Maintenance of Existing gauging network of manual water level measurement 3. Installation of new manual water level gauge stations 4. Maintenance of existing gauging network and real-time data monitoring system of automated water level measuring system. 5. Discharge measurement & maintain the data base. | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
20 | Selected drainage improvement work in Piliyandala Master Plan | 3.5 | 12 Months | Kesbewa divisional Secretariat |  | - | - | 1. To mitigate localized flood. 2. To reduce unauthorized filling. 3. To promote agricultural work in the acquired land. |  |  | Preparation of Feasibility Report | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
21 | Essential works in Mudun Ela Flood Mitigation & Environment Protection Activities | 4.5 | 12 Months | Gampaha Divisional Secretarial, Wattala Pradeshiya Sabhawa, Kelaniya Pradeshiya Sabhawa, Biyagama Pradeshiya Sabhawa |  | - | - | 1. Flood reduction. 2. Release of new lands. |  |  | Details Design and Obtaining NPD Approval Surveying of Canals. | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
22 | Selected drainage improvements and designs of Bidunu Ela Drainage Improvement Project | 3.5 | 12 Months | Panadura Divisional Secretarial, Thalapathpitiya South, Molligoda Wadduwa East, Molligoda North, Kuda Wadduwa, Molligoda South |  | - | - | 1. Mitigate the local flood issues. 2. Restore paddy cultivation. 3.Uplift the socio economic condition of the people living in this area. |  |  | Details Design and Obtaining NPD Approval Surveying of Canals. | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
23 | Preparation of drainage plans for selected flood prone areas in Western Province | 8.5 | 12 Months | Based on the request made by any Institution in Western Province. |  | - | - | 1. Mitigate the local flood issues. |  |  | 1 . Site inspection. 2. Drainage study. 3. Formation of drainage plan. 4. Proposal for solving localized flood. | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
24 | Oliyamulla Storm Water Drainage and Environment Improvement Project | 3000 | 7 Years | 175 Thelangapatha -Wattala DS and 174 C Meegahawatta - Kelaniya DS |  | - | - | 1. Preventing flood damages to houses, business premises, roads and cultivation. (Pethiyagoda, Wedamulla, Dalugama, Peliyagoda & Mudun Ela) 2. Saving on social welfare expenditure on flood relief. Saving on health expenditure. 3. Healthy flood free environment leads to uplift socio economic status of the people. 4. Prevention of income loses of the people due to floods. 5. Increasing land value 6. Availability of job opportunities in industrial/commercial establishments which will be proposed in reclaimed land. | SLLDC | SLLDC Head Office | 1. Construction of Pumping Stations I and II 2. Reconstruction of Bridge No 1/3 of Peliyagoda Puttalam Road. 3. Resettlement Works 4. Lake Dredging and Down stream improvement. | Deputy General Manager (Construction) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
25 | Drainage improvements & taking remedial measures for the flood related issues in public places on request of disaster situation | 5 (For 2025), 0.000 (Allocation for 2025 January - April ) | 12 Months | Based on the request made by any Institution in outside Western Province. |  | 0 | 0 | 1. Mitigate the local flood issues. | SLLDC | SLLDC head office (R&D) | 1 . Site inspection. 2. Drainage study. 3. Formation of drainage plan. 4. Proposal for solving localized flood. | - | - | 1. When requests are received by the public or local authorities, the drainage proposal is made to a public place.
26 | Preparation of urban drainage plans in Matara area on request by UDA and local authorities | 0.25 | 12 Months | Based on the request made by UDA and local authorities |  | 0 | 0 | 1. Mitigate the local flood issues. | SLLDC | SLLDC head office (R&D) | 1 . Site inspection. 2. Drainage study. 3. Formation of drainage plan. 4. Proposal for master drainage plans. | - | - | 1. Site visit, data collection done. 2. Draft conceptual drainage proposal submitted. 3. Hydrology modeling & study.
27 | Feasibility Study in Hettige Ela Catchment - Kaduwela | 2 | 8 Months | Kaduwela | GOSL | 0 | 0 | Manage the disasters that occurs due to the flooding in the area of Kalani Ganga | SLLDC | SLLDC Head Office | Develop an Urban flood management plan for Kaduwela - Hettige Ela Catchment | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
28 | Proposed strategy for the preservation of flood sensitive areas in Mudun Ela basin | 7 | 8 Months | Mudun Ela sub watershed of Kelaniya divisional secretariat. |  | - | - | 1. Mitigate the local flood issues. | SLLDC | SLLDC head office | Digitized retention map for Mudun Ela basin. | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
29 | Strategy for Protection of Flood Sensitive Areas in Bindunu Ela Basin. | 5 | 8 Months | Bindunu Ela sub watershed of Panadura Divisional Secretarial. |  | - | - | 1. Mitigate the local flood issues. | SLLDC | SLLDC head office | Digitized retention map for Bindunu Ela basin. | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
30 | Wetland Conservation Strategy Through the Generation of Digitized Maps for Identified Flood-Sensitive Areas in the Piliyandala Urban Area. | 6 | 8 Months | Piliyandala sub watershed of Weras Ganga at Piliyandala bypass road at Kesbewa divisional Secretariat. |  | - | - | 1. Mitigate the local flood issues. | SLLDC | SLLDC head office | Digitized retention map for Piliyandala area. | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
31 | Preparation of digitized maps for protected retention areas in Madiwela East sub-catchment. | 8.4 | 8 Months | Piliyandala sub watershed of Weras Ganga at Piliyandala bypass road at Kesbewa divisional Secretariat. |  | - | - | 1. Mitigate the local flood issues. | SLLDC | SLLDC head office | Digitized retention map for Piliyandala area. | Deputy General Manager (UrWM) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
32 | Design of Proposed storm water Drainage & Public facility improvement project at Beruwela, Dickwella. | 6 | 8 Months | District: Matara Divisional Secretariat Division:Dickwella Grama Niladhari Divisions: Wewrukannala, Wewurukannala, Dickwella Muslim Yonakapura East, Dickwella Muslim Yonakapura West, Wattegama, Wattegama North, Dickwella South, Dickwella Central. |  | - | - | * Control flooding. * Improve tourism. * Upgrade household income. * Improve mental & physical health of public. | SLLDC | SLLDC head office | * Pre-Feasibility * Feasibility * Detailed Design * Initial Environmental Assessment (IEE) * Environmental Impact Assessment (EIA) * Disaster Risk Assessment Archeological Clearance (If necessary) * Land Clearance from relevant parties * Social Impact Assessment * Other (specify) | Deputy General Manager (R&D) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -
33 | Use of Wetlands for economic development of Colombo Wetland City Stage 01: Feasibility study on introducing a sustainable eco-tourism master plan for Colombo Wetland City | 10 | 1 Year | Colombo Wetlands |  | - | - | Creation of new income sources to SLLDC Creation of livelihoods associated with the wetland Parks Increase the land value in the area Support for the urban tourism of the country | SLLDC | SLLDC head office | Create beautiful locations in wetlands Create easy access to wetlands for everyone Encroachment Prevention related wetlands Maintenance Awareness about Wetlands | Deputy General Manager (WM ) | Sri Lanka Land Development Corporation, No 03, Welikada, Rajagiriya. | -

## New project
Disclosure of Information on Development Projects for General Public as a Right of the People - 2024/2025
New Projects as at 01.09.2025 (Project which is approved (Cabinet/NPD) or submitted to Cabinet/NPD for approval or work to be started in 2025)
Executing Agency |  | : Ministry of Urban Development, Construction and Housing
# | Name of the Project | Total Estimated Project Cost (Rs.Mn.) | Expected Duration of the Project | Location of the Project (Grama Niladhari Division /Divisional Secretariat Division /District Secretariat Division) | Financing Agency (GOSL/ Foreign/ PPP) | Loan |  | Expected Benefits of the Project | Implementing Agency | Location of Project Management Unit | Project Components/ Activities | Approval Details |  | Present Status/ Stage of the Project
[6 empty] | Amount (Rs.Mn.) | Interest Rate (%) |  |  |  |  | Cabinet (Date & Number) | NPD (Date & Number)
Name of the Department/Institution/Project :01. Urban Development Authority (UDA)
1 | Dimbulagala Entrance Landscape Development Project | 9.8 | 6/15/2025 - 6/14/2026 | DS Division: Dimbulagala / GN Division: 211 - Dimbulagala | GOSL |  |  | *Preservation and promotion cultural heritage while making attractive to local and foreign tourists, *Enhancing the aesthetic appeal of the "Ahas Maligawa"Entrance.*Construction of new sanitary facilities catering to public needs.*Construction of seating and pathways to provide comfort and develop accessibility for pilgrims.*Redevelopment of the "Ahas Maligawa"entrance featured with drinking water facility as"Pinthaliya"*Improvement of Storm water drainage system | Urban Development Authority | Environment and Landscape Division, Urban Development Authority | Demolition Work, Earth Works, Landscape Works, Retaining Walls, Water Supply, Sewerage and Drainage Work , Rectification of Toilet Block |  | Letter no - 84 2025.04.21 Secretary approval. | Procurement process is on progress
2 | Development of Pitakotuwa Bodiraja mawatha (100 Feet Road) | 9.57 | 90 days | Near Central Bus Stand -Pettah | GOSL | ----- | ---- | Improve the pedestrian connection of the central bus stand and the central market. | UDA | Project Management Division /UDA | - Pedestrian Pathway - Street Lights - Tree line | ---- | Letter no - 249 2025.05.15 Secretary approval. | Tendering in progress
Name of the Department/Institution/Project : 02. Urban Settlement Development Authority (USDA)
1 | Wattala Walisara Housing Project | 8342.92 | 2025-2027 | Alapitiwala, Wattala DSD, Gampaha District | PPP |  |  | Provision of 408 apartment type housing units and integration of new development with the existing infrastructure facilities by 2025 Generate income to the USDA by providing the said project and hereby reducing the dependency on government grants by 2027 | Urban Settlement Development Authority | 9th floor, Sethsiripaya stage1,Baththaramulla | 1. Obtaining preliminary clearances and approval i. Preliminary Clearances (UDA/NBRO/ Civil Aviation Authority/ LECO/ NWS&DB/ CEA etc. 2. Cost associated with Procurement Process 3. Water & Electricity Connection/ Road 4. Project Consultancy Fees i. Design Review ii. Consultancy Fee 5. Marketing Cost 6. Project Management Cost 7. Land Clearance/ deforestation/ Boundary post and other activities | 2021.03.08 අමප/21/0291/306/018 | 2022.08.25 NP/UDH/UD/USDA/2023-PI | * Renewal of PPC has been obtained *Water Clearance from the NWS&DB has been obtained * Paper advertisement on tender call is published on 2025.02.24 (Dinamina, Daily News, Thinakara). Tender issued on the dates of 2025.02.25-2025.04.29 and Pre bid meeting has been held on 2025.03.12. One bid has issued but no bids were submitted on closing date. Hence, SCANC granted to recall procurement process. * According to the new procurement bidding documents were issued during 2025.08.11-2025.09.01. *Pre-bid meeting was held on 2025.08.18. *Bid opening will be scheduled on 2025.09.22 * The ownership of the land has been transferred to the USDA under the section 6(1) of Land Ordinance Act. * Valuation of the land has been obtained * Survey plan has been approved by the local authority * Names in the assessment register has been changed to the ownership of USDA and the assessment numbers has been obtained. *contour plan has been prepared.
2 | Nittambuwa Orchard Watta Housing | 1480 | 2025-2027 | 348E, Malwaththa GND/ Attanagalla DSD/ Gampaha District | PPP |  |  | Provision of 130 housing facilities for devoted senior citizens Develop infrastructure facilities and services within the city Strengthening the elderly's access to health services at home or in community health centers Improving the health conditions of the community Increasing the employment opportunities related to health sector in the Sri Lanka | Urban Settlement Development Authority | 9th floor, Sethsiripaya stage1,Baththaramulla | 1. Obtaining preliminary clearances and approval i. Preliminary Clearances (UDA/NBRO/ Civil Aviation Authority/ LECO/ NWS&DB/ CEA etc.) 2. Cost associated with Procurement Process 3. Water & Electricity Connection/ Road 4. Project Consultancy Fees i. Design Review ii. Consultancy Fee 5. Marketing Cost 6. Project Management Cost 7. Land Clearance/ deforestation/ Boundary post and other activities | 2021.05.24 අමප/21/0911/340/018 2021.06.01 අමප/21/0830/306/051 | 2024.04.18 NP/UDH/UD/USDA/2023-P2 | * SCANC recommended to request for further verification obtained regarding the current performance financial standing of the bidder from CIDA, line Ministry, Ministry of Public Administration, Provincial Council and Local Government and Ministry of Transport, Highways, Port. * The ownership of the land has been transferred to the USDA by purchasing. (purchased from LRC) * Valuation of the land has been obtained * Survey plan has been approved by the local authority * Names in the assessment register has been changed to the ownership of USDA and the assessment numbers has been obtained.
3 | Sri Jayawardhanapura Kotte Mix development Project | 8278 | 2025-2028 | Athul kotte West Sri JayawardhanapuraGND Jayawardhanapura Kotte DSD Colombo District | PPP |  |  | Provision of 160 apartment-type housing units with Office spaces, commercial spaces and integration of new development with the existing infrastructure facilities by 2027 | Urban Settlement Development Authority | 9th floor, Sethsiripaya stage1,Baththaramulla | 1. Obtaining preliminary clearances and approval i. Preliminary Clearances (UDA/NBRO/ Civil Aviation Authority/ LECO/ NWS&DB/ CEA etc.) 2. Cost associated with Procurement Process 3. Water & Electricity Connection/ Road 4. Project Consultancy Fees 5. i. Design Review ii. Consultancy Fee 6. Marketing Cost 7. Project Management Cost 8.Post Office Relocation Cost 9. Land Matters i. Obtaining approvals for preliminary plans and for land subdivisions from Local Authorities. ii. Inserting name in the assessment register/Obtaining Street Line and Non vesting certificate | 2021.08.17 අමප/21/0911/340/018 | 2021.11.30 NP/UDH/UD/USDA-2024-P2 | * Applied renewal of PPC * Requested for appointment of the PC * Applied for land subdivision application of Sri Jayewardenepura MC * The project details have been presented to the Division Coordination committee and District Coordination Committee * The ownership of the land has been transferred to the USDA under the section 6(1) of Land Ordinance Act. * Valuation of the land has been obtained for the year 2023 * Names in the assessment register has been changed to the ownership of USDA and the assessment numbers has been obtained. * The Non vesting and Ownership certificate has been obtained * contour plan has been prepared.
4 | Thuduwegoda Housing Project | 5884.45 | 2025-2028 | Hikkaduwa Nagarikaya GND Hikkaduwa DSD Galle District | PPP |  |  | Provision of 550 ft2 housing units for underserved 32 families who live in this existing site by 2022 Provision opportunities for varied housing forms and levels of affordability through 160 innovative housing options targeting middle income and lower middle income groups of the people those live in Galle District and do not have any permanent housing solution by 2024 Create a unique neighborhood identity by landscaping the site and constructing recreational spaces with children’s play areas (covering the extent of 0.71 Ha) Provision one to one parking in new development to address community concerns with parking | Urban Settlement Development Authority | 9th floor, Sethsiripaya stage1,Baththaramulla | 1. Obtaining preliminary clearances and approval i. Preliminary Clearances (UDA/NBRO/ Civil Aviation Authority/ LECO/ NWS&DB/ CEA etc.) 2. Cost associated with Procurement Process 3. Water & Electricity Connection/ Road 4. Relocation Cost 5. Land Matters - Vesting under 6(1) i. Preparing O Diagram from Survey Department ii. Preparing the drawing according to the Thuduwegoda land's preliminary plan through a licensed surveyor. iii. Obtaining approvals for preliminary plans and for land subdivisions from Local Authorities and UDA. iv. Inserting name in the assessment register/Obtaining Street Line and Non vesting certificate v. Obtaining Land Valuation vi. Clearing up the Land 6. Land Matters - Accusation i. Preparation of Advanced Tracing from Survey Department ii. Obtaining Land Valuation iii. Cost of compensation for land acquisition process. (The amount will be decided according to the Land Acquisition act. And the cost will be incurred in the relevant step of the land acquisition act.) iv. Preparing the drawing according to the Thuduwegoda land's preliminary plan through a licensed surveyor. v. Obtaining approvals for preliminary plans and for land subdivisions from Local Authorities. vi. Clearing up the Land and setting Boundary post | 2022.07.15 අමප/22/0939/520/016 | 2021.01.05 NP/PP/PUT/HOU/2020/07 | * Submitted NPD recommendation for Land Commissioner General Department * Vesting of land process is on progress * Land acquisition is on progress
5 | Kaduwela Housing Project | 4020 | 2025-2028 | Kaduwela GND Kaduwela DSD Colombo District | PPP |  |  | This project provides advantages for a lot of parties like Kaduwela Local Authority to increase their revenues, the surrounding economical activities and this is a good opportunity for the people who are willing to buy a home at an affordable price from the core area of CBD of Colombo. Developing this site, there have major outcomes as fallow. ▪ Provide 108 housing units with a comfortable physical environment. ▪ 120 parking slots allocated for the building uses in the same building. ▪ 6 apartments for the accommodation purpose of the postal department. ▪ Provide office space for the Post office of Kaduwela. ▪ Provide space for the newly proposed Postal tanning institute with allocated spaces for four lecture halls, one auditorium, one IT lab, a Lunchroom, and two lecture rooms. ▪ The profit of this project is funded to our fund and thereby to success in our endeavor to become an independent institution without depending on government funds. | Urban Settlement Development Authority | 9th floor, Sethsiripaya stage1, Baththaramulla | 1. Obtaining preliminary clearances and approval i. Preliminary Clearances (UDA/NBRO/ Civil Aviation Authority/ LECO/ NWS&DB/ CEA etc.) 2. Cost associated with Procurement Process 3. Water & Electricity Connection/ Road 4. Relocation Cost 5. Land Matters i. Preparing O Diagram from Survey Department ii. Preparing the drawing according to the kaduwela post office land's preliminary plan through a licensed surveyor. iii. Obtaining approvals for preliminary plans and for land subdivisions from Local Authorities. iv. Inserting name in the assessment register/Obtaining Street Line and Non vesting certificate | 2022.03.15 අමප/22/0332/306/025 | 2022.08.19 NP/UDH/UD/USDA-2022-P1 | * Obtained Governor's Approval *Documents have been sent to Land Commissioner General Department * The project details have been presented to the Division Coordination committee and District Coordination Committee * Valuation of the land has been obtained * Vesting of land process is on progress *Preliminary survey plan and the contour plan has been prepared.
6 | Athurugiriya Housing Project | 55.15 |  | No 487A, Shanthalokagama GN Kaduwela DSD Colombo District | PPP |  |  |  | Urban Settlement Development Authority | 9th floor, Sethsiripaya stage1, Baththaramulla | 1. Land Matters i. Obtaining Land Valuation ii. Preparing the drawing according to the Huvibertwatta land's preliminary plan through a licensed surveyor. iii. Cost of compensation for land acquisition process. (The amount will be decided according to the Land Acquisition act. And the cost will be incurred in the relevant step of the land acquisition act.) iv. Obtaining approvals for preliminary plans and for land subdivisions from Local Authorities and UDA. v. Land Clearance/ deforestation/ Boundary post and other activities |  |  | * Land acquisition is on progress