## On going Projects
Disclosure of Information on Development Projects for General Public as a Right of the People - 2023
On going Projects as at 31.05.2023 (Project which is awarded on or before 31.05.2023 and work started/ongoing)
Executing Agency |  | : State Ministry of Urban Development
Name of the Department/Institution/Project : Urban Development Authority
# | Name of the Project | Total Estimated Project Cost (Rs.Mn.) | Expected Duration of the Project | Location of the Project (Grama Niladhari Division /Divisional Secretariat Division /District Secretariat Division) | Financing Agency (GOSL/ Foreign) | Loan |  | Expected Benefits of the Project | Implementing Agency | Location of Project Management Unit | Project Components/ Activities | Contactor Details |  | Value of the Contract (Rs.Mn.)
[6 empty] | Amount (Rs.Mn.) | Interest Rate (%) |  |  |  |  | Name | Address
1. Siyak Nagara/ Urban Infrastructure & Township Development Programm
1 | Nature corridor development along Nanu Oya stream at Nuwara Eliya | 120 | 5/1/2021 - 05/02/2023 | Nuwara Eliya DS | GoSL | - | - | Landscape development | UDA | Project Management Division, UDA | Landscaping | M/S Malwatta | 119, Gampola Rd, Ulapane | 107.3
2 | Beach park Development at Nintavur Phase - I | 80 | 22/07/2021 17/04/2023 | Ampara DS | GoSL | - | - | Sustained tourisum development samall scale economic development | UDA | Project Management Division, UDA | Beach park | Central Engineering Services (Pvt) Ltd. (CESL) | No. 415, Bauddhaloka Mawatha, Colombo 07 | 83.7
3 | Green Infrastructure Development along – “Vallaivelie” – Jogging Track Point Pedro | 70.2 | 9/1/2021 - 2/15/2023 | Jaffna DS | GoSL | - | - | Promoting physical fitness and good health and increasing recreational facility among the people | UDA | Project Management Division, UDA | Walk way Track | NEMO Construction | Negombo Road, Paliyagoda | 70.17 original TEC. Require 5mn to complete this project to a usable quality
4 | Redevelopment project of Rajapihilla Urban Park at Kurunegala (phase II) | 204.21 | 2021-08-21 2023-05-02 | Kurunegala DS | GoSL | - | - | Providing recreational facilities | UDA | Project Management Division, UDA | Completion of urban park | Asiri Building Construction | 418, Udupila, Delgoda | 40.53
5 | Holuwagoda Agroecological Park phase I&II | 450.56 | 2021-08-05 2023-02-08 | Galle DS | GoSL | - | - | Providing recreational facilities | UDA | Project Management Division, UDA | Completion of jogging track | SLLDC | 4 Sri Jayawardenepura Mawatha Welikada, Sri Jayawardenepura Kotte | 132
6 | Development of public market at Avissawella | 167.6 | 2021-08-02 2023-06-30 | Colombo DS | GoSL | - | - | Providing market facilities for venders | UDA | Project Management Division, UDA | Completion of market | Daninton Construction | 854, Galle Rd, Katukurunda, Kaluthara. | 167
7 | Development of public market at Gampaha (stage II) | 420 | 9/25/2021-3/25/2023 | Gampaha DS | GoSL | - | - | Development of public market | UDA | Project Management Division, UDA | Completion of market | Sripalie Construction (Pvt.) Ltd | No. 06, S.H. Dahanayake Mawatha, Kaluwella, Galle | 420
8 | Redevelopment of Oruthota walking path at Gampaha | 58.62 | 2021-06-26 2023-03-20 | Gampaha DS | GoSL | - | - | City beatification | UDA | Project Management Division, UDA | Walk way Track | Sri Lanka Land Development Corporation | Welikada, Rajagiriya. | 54.3
9 | Department of Panadura market and multipurpose building | 539.2 | 2021-09-30 2023-12-31 | Kaluthara DS | GoSL | - | - | Providing Building Facilities for venders | UDA | Project Management Division, UDA | Public market | Mode Enginering | 467, 1 Havelock Rd, Colombo 05 | 539.2

## New project
Disclosure of Information on Development Projects for General Public as a Right of the People - 2023
New Projects as at 31.05.2023 (Project which is approved (Cabinet/NPD) or submitted to Cabinet/NPD for approval or work to be started in 2023)
Executing Agency |  | : State Ministry of Urban Development
Name of the Department/Institution/Project : Urban Development Authority
# | Name of the Project | Total Estimated Project Cost (Rs.Mn.) | Expected Duration of the Project | Location of the Project (Grama Niladhari Division /Divisional Secretariat Division /District Secretariat Division) | Financing Agency (GOSL/ Foreign/ PPP) | Loan |  | Expected Benefits of the Project | Implementing Agency | Location of Project Management Unit | Project Components/ Activities | Approval Details |  | Present Status/ Stage of the Project
[6 empty] | Amount (Rs.Mn.) | Interest Rate (%) |  |  |  |  | Cabinet (Date & Number) | NPD (Date & Number)
1. Siyak Nagara/ Urban Infrastructure & Township Development Programm
1 | Proposed weekly fair and multi functional building at Walapane (stage II) | 180 | 2023-03-01 2023-12-01 | Nuwara Eliya DS | GoSL | - | - | Provide Facilities for Venders and Public | UDA | Project Management Division, UDA | Nanu Oya river bank stabilization |  | At the meeting held at Ministry of finance, on 30.11.2022 it was agreed to temporary susupend stage one of the project as there is no possibility to granting additional.
2 | Madhu bus stand development | 250 | 2023-01-01 2024-07-01 | Mullativu DS | GoSL | - | - | Providing bus parking facilities | UDA | Project Management Division, UDA | Land development work, asphalt area and construction of sanitary block |  | concept paper was submitted.Approval was not granted for allocation of funds by DNP by their letter no; NP/UDH/UD/UDA/2022-P6and dated 28.11.2022
3 | Completion of bus stand at Mullativu (stage II) - (continuation) | 170 | 2023-05-06 2023-11-15 | Mullativu DS | GoSL | - | - | Providing bus parking facilities | UDA | Project Management Division, UDA | Completion of 4,455 sq.ft. area bus stand (balance part of the existing bus stand) with 8 bus bays, 2 cafeterias, waiting areas and time keeper's room for both private and CTB |  | Concept paper was submitted.Approval is pending | Architectural and Engineering drawings were completed. Preparation of BOQ is in progress
4 | Public fair redevelopment project at Thambuttegama (stage I) | 250 | 2023-03-01 2024-12-01 | Thambuttegama Ps | GoSL | - | - | Provide Facilities for Venders and Public | UDA | Project Management Division, UDA | 100% completion of 5,500 sq.ft. weekly fair, 1,000m2 paving work, improving 7,500 sq.ft. area of old stalls, 500 ft. drainage work and 600 perch vehicle park |  | concept paper was submitted.Approval was not granted for allocation of funds by DNP by their letter no; NP/UDH/UD/UDA/2022-P6and dated 28.11.2022
5 | Public fair development at Alawwa (stage II) | 50 | 2023-03-01 2024-09-01 | Kurunegala DS | GoSL | - | - | Provide Facilities for Venders and Public | UDA | Project Management Division, UDA | 100% completion of existing 200m length access road widening and completion of balance landscaping and finishing work of weekly fair |  | At the meeting held at Ministry of finance, on 30.11.2022 it was agreed to complete the reduced activities of the scope that widen the main access road and complete the parking area in year 2023. | Architectural and Engineering drawings, BOQ were completed.
6 | Proposed parking and pedestrian facilities improvement project at Alawwa (stage II) | 100 | 2023-03-01 2024-12-01 | Kurunegala DS | GoSL | - | - | Construction of the 9m width pavement parallel to drain of Alawwa - Gorilla main street | UDA | Project Management Division, UDA | 100% completion of construction of 9m wide payments and 500m length |  | Submitted the proposal and recommendation from Ministry to DNP by letter number MUD&H/UDD/P&M-4/PP/2023 and dated 21.03,2021. DNP returned the documents due to lack of certain information. Resubmitted the details. | Architectural and Engineering drawings were completed. Preparation of BOQ is in progress
7 | Warakapola bus stand (stage II) | 280 | 2023-04-25 2024-04-24 | Warakapola Ps | GoSL | - | - | Providing bus parking facilities | UDA | Project Management Division, UDA | City beatification |  | 2021/09/21 NPD/BA/2021 | Stage I Completed
8 | Boralesgamuwa multipurpose building (stage III) | 192 | 10/03/2023 24/12/2024 | Boralesgamuwa Ps | GoSL | - | - | Construction of public facility building for the Urban Council | UDA | Project Management Division, UDA | Multi purpose building | _ | 2019.09.18 | Tender Document Submit to Ministry
9 | Peralanda wetland area recreational development project (stage III) | 154.5 | 2023-03-02 2023-11-30 | Gampaha DS | GoSL | - | - | Providing recreational facilities | UDA | Project Management Division, UDA | Completion of park |  | Concept paper was submitted.
10 | Public market Minuwangoda (stage III) | 30 | 2023-02-14 2023-12-14 | Gampaha DS | GoSL | - | - | Providing market facilities for venders | UDA | Project Management Division, UDA | Completion of market | _ | 2018.09.04 | Tender Documents submit to Ministry
11 | Bus stand at Ganemulla | 99.18 |  | Gampaha DS | GoSL | - | - | Providing bus parking facilities | UDA | Project Management Division, UDA | Bus stand development | _ | 2023.03.29 ( Pending Final Approval) | Design stated